## Sheet1
ID | Code | Story | Requirement | Size | Risk | Completed By
1 | US 01.01.01 | As an entrant, I want to join the waiting list for a specific event | The software shall add the entrant to a waiting collection of other entrants per open event | 1 | high | William
2 | US 01.01.02 | As an entrant, I want to leave the waiting list for a specific event | The software shall remove entrants from a waiting collection of other entrants per open event | 1 | high | William
3 | US 01.01.03 | As an entrant, I want to be able to see a list of events that I can join the waiting list for. | The software should display open events with open waiting collections | 1 | medium | William
4 | US 01.01.04 | As an entrant, I want to filter events based on my interests and availability. | The software may filter open events by entrants' interests and availablility before displaying | 3 | low | William
5 | US 01.02.01 | As an entrant, I want to provide my personal information such as name, email and optional phone number in the app | The software may store entrants' name, email and phone number in a profile | 2 | low | William
6 | US 01.02.02 | As an entrant I want to update information such as name, email and contact information on my profile | The software may permit entrants to modify their name, email and phone number in their profile | 1 | low | William
7 | US 01.02.03 | As an entrant, I want to have a history of events I have registered for, whether I was selected or not. | The software should record entrants' applications and their lottery results | 1 | medium | William
8 | US 01.02.04 | As an entrant, I want to delete my profile if I no longer wish to use the app. | The software may permit entrants to delete their profile | 2 | low | William
9 | US 01.04.01 | As an entrant I want to receive notification when I am chosen to participate from the waiting list (when I "win" the lottery) | The software shall notify entrants if they win the lottery for an event | 2 | high | Ben
10 | US 01.04.02 | As an entrant I want to receive notification of when I am not chosen on the app (when I "lose" the lottery) | The software shall notify entrants if they lose the lottery for an event | 2 | medium | Ben
11 | US 01.04.03 | As an entrant I want to opt out of receiving notifications from organizers and admins | The software should not send notifications if the entrant is not opted in for that organizer or admin | 1 | low | Ben
12 | US 01.05.01 | As an entrant I want another chance to be chosen from the waiting list if a selected user declines an invitation to sign up. | The software shall select another entrant if a winner declines their lottery result | 1 | low | Ben
13 | US 01.05.02 | As an entrant I want to be able to accept the invitation to register/sign up when chosen to participate in an event. | The software shall send an acceptable invitation to entrants that are chosen to enter an event | 2 | high | Ben
14 | US 01.05.03 | As an entrant I want to be able to decline an invitation when chosen to participate in an event. | The software must provide the entrant the opportunity to decline the invitation to enter an event | 1 | medium | Ben
15 | US 01.05.04 | As an entrant, I want to know how many total entrants are on the waiting list for an event. | The software should record and display the number of entrants per event | 1 | low | Ben
16 | US 01.05.05 | As an entrant, I want to be informed about the criteria or guidelines for the lottery selection process. | The software should display information about the lottery selection process | 1 | low | Ben
17 | US 01.06.01 | As an entrant I want to view event details within the app by scanning the promotional QR code. | The software shall let entrants scan a QR code to open event details | 3 | high | Xindi
18 | US 01.06.02 | As an entrant I want to be able to be sign up for an event by from the event details. | The software shall let users create an account to register for events. | 2 | high | Xindi
19 | US 01.07.01 | As an entrant, I want to be identified by my device, so that I don't have to use a username and password. | The software should show each entrant’s display name in event pages and leaderboards. | 1 | medium | Xindi
20 | US 02.01.01 | As an organizer I want to create a new event and generate a unique promotional QR code that links to the event description and event poster in the app. | The software shall let organizers create new events with name, date, and info. | 3 | high | Xindi
21 | US 02.01.04 | As an organizer, I want to set a registration period. | The software shall let organizers set a closing date for registration. | 2 | high | Xindi
22 | US 02.02.01 | As an organizer I want to view the list of entrants who joined my event waiting list | The software shall show organizers a list of all registered entrants. | 2 | high | Xindi
23 | US 02.02.02 | As an organizer I want to see on a map where entrants joined my event waiting list from. | The software should show a map with the locations where entrants joined the waiting list. | 3 | medium | Xindi
24 | US 02.02.03 | As an organizer I want to enable or disable the geolocation requirement for my event. | The software should let organizers turn the geolocation requirement on or off. | 2 | medium | Xindi
25 | US 02.03.01 | As an organizer I want to OPTIONALLY limit the number of entrants who can join my waiting list. | The software should allow organizers to set size limits on waiting collection of events | 1 | medium | Justin
26 | US 02.04.01 | As an organizer I want to upload an event poster to the event details page to provide visual information to entrants. | The software should allow organizers to upload images/posters on an event details page | 1 | low | Justin
27 | US 02.04.02 | As an organizer I want to update an event poster to provide visual information to entrants. | The software should allow organizers to update previously uploaded images/posters on an event details page | 1 | low | Justin
28 | US 02.05.01 | As an organizer I want to send a notification to chosen entrants to sign up for events. This is the notification that they "won" the lottery. | The software should notify entrants if they win the lottery for an event | 2 | high | Justin
29 | US 02.05.02 | As an organizer I want to set the system to sample a specified number of attendees to register for the event. | The software should randomly select a specified number of attendees to register for an event | 1 | high | Justin
30 | US 02.05.03 | As an organizer I want to be able to draw a replacement applicant from the pooling system when a previously selected applicant cancels or rejects the invitation. | The software should select another applicant from the waitlist if a previously selected applicant rejects their invintation | 2 | high | Justin
31 | US 02.06.01 | As an organizer I want to view a list of all chosen entrants who are invited to apply. | The software should allow organizers to see a list of chosen entrants who are able to apply for an event | 1 | low | Justin
32 | US 02.06.02 | As an organizer I want to see a list of all the cancelled entrants. | The software should allow organizers to see a list of cancelled entrants | 1 | low | Justin
33 | US 02.06.03 | As an organizer I want to see a final list of entrants who enrolled for the event. | The software should allow organizers to see the entrants list of the events they host | 1 | low | Eric
34 | US 02.06.04 | As an organizer I want to cancel entrants that did not sign up for the event | The software should allow organizers to cancel the entrants who didnt sign up | 2 | medium | Eric
35 | US 02.06.05 | As an organizer I want to export a final list of entrants who enrolled for the event in CSV format. | The software should allow organizers to export a CSV format list of entrants who enrolled | 1 | low | Eric
36 | US 02.07.01 | As an organizer I want to send notifications to all entrants on the waiting list | The software should allow organizers to send notifications to entrants on the event wating list | 3 | low | Eric
37 | US 02.07.02 | As an organizer I want to send notifications to all selected entrants | The software should allow organizers to send messages to all selected entrants | 3 | medium | Eric
38 | US 02.07.03 | As an organizer I want to send a notification to all cancelled entrants | The software should allow organizers to send messages to all cancelled entrants | 3 | low | Eric
39 | US 03.01.01 | As an administrator, I want to be able to remove events. | The software should allow administrators to remove events | 1 | high | Eric
40 | US 03.02.01 | As an administrator, I want to be able to remove profiles. | The software should allow administrators to remove profiles | 1 | high | Eric
41 | US 03.03.01 | As an administrator, I want to be able to remove images.
42 | US 03.04.01 | As an administrator, I want to be able to browse events.
43 | US 03.05.01 | As an administrator, I want to be able to browse profiles.
44 | US 03.06.01 | As an administrator, I want to be able to browse images that are uploaded so I can remove them if necessary.
45 | US 03.07.01 | As an administrator I want to remove organizers that violate app policy.
46 | US 03.08.01 | As an administrator, I want to review logs of all notifications sent to entrants by organizers.